## Sheet1
MSUP VM Notification Number | Forest | Ranger District | Work Class Notification (most conservative) | SCE District | Geographic Area | Control Sheet Number | Fulcrum ID Number/ Arbora Salesforce.com ID / S123 OID | Tree DBH (in) | Tree Height (ft) | Tree Species | Quantity | Type of Work (e.g., hazard tree removal, corridor maintenance, new or heavy pole and/or tower brushing/clearing) | Estimated Work Schedule | Vegetation Clearing (describe activities or say none) | Access Route | List of Equipment to be Used (anticipate equipment based on project description) | Latitude | Longitude | Review Records | Biological Resource Review (presence/absence, resource description if appropriate) | Biological RPMs | Heritage Resources Review (Reported in the confidential heritage notification table) | Waters/Wetlands Work Class Review (per MSUP O&M plan) | Waters/Wetlands Review (presence/absence, resource description if appropriate) | Waters/Wetlands RPMs
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | R05036866001 | a0p4v00000aXnGX | 17 | 18 | Fir-White | 1 | Green Routine Line Clearing Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2793 | -119.1112 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located approximately 280-ft NW and within the designated RCA buffer (300 feet on each side of the stream from bank full edge of stream) a potentially jurisdictional feature (perennial drainage [Rancheria Creek]) based on desktop analysis of the anticipated work area; however, no impacts to Waters/Wetlands resources are anticipated. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130208001 | a0p4v00000aXnpw | 23 | 85 | Pine-Lodgepole | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2737 | -119.1183 | Sierra Marten - USFS (1978) 0.20-mi ¦ USFS (1991) 0.45-mi ¦ USFS (1991) 0.70-mi ¦ USFS (1991) 0.75-mi ¦ USFS (1999) 0.80-mi ¦ USFS (2001) 0.19-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located approximately 5-ft W and within the designated RCA buffer (150 feet on each side, measured from bank full edge) a potentially jurisdictional feature (intermittent drainage) based on desktop analysis of the anticipated work area. None to minimal impacts to Waters/Wetlands resources are anticipated; however, a Waters Monitor is required to be onsite during work activities to ensure adherence to MSUP Protection Measures. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply. W/W Monitor Required.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130214001 | a0p4v00000Zw1ag | 20 | 65 | Pine-Lodgepole | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2862 | -119.1038 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Great Gray Owl - USFS (2018) 0.45-mi - sample area Willow Flycatcher - USFS (1995) 0.39-mi ¦ USFS (1995) 0.43-mi ¦ USFS (1995) 0.56-mi ¦ USFS (1995) 0.69-mi ¦ USFS (1995) 0.70-mi ¦ USFS (1995) 0.72-mi - sample areas Sierra Marten - CNDDB (1989) 0.69-mi ¦ USFS (1991) 0.28-mi ¦ USFS (1991) 0.47-mi ¦ USFS (1991) 0.88-mi ¦ USFS (1991) 0.99-mi ¦ USFS (1999) 0.45-mi ¦ USFS (2001) 0.59-mi ¦ USFS (2002) 0.50-mi ¦ USFS (2004) 0.50-mi ¦ USFS (2005) 0.50-mi ¦ USFS (2006) 0.50-mi ¦ USFS (2007) 0.50-mi ¦ USFS (2008) 0.50-mi ¦ USFS (2011) 0.76-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located outside of the SNF RCA layer, and approximately 25-ft E a potentially jurisdictional feature (ephemeral drainage) based on desktop analysis of the anticipated work area; however, no impacts to Waters/Wetlands resources are anticipated. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130214002 | a0p4v00000aXnG3 | 18 | 62 | Pine-Lodgepole | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2862 | -119.1037 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Great Gray Owl - USFS (2018) 0.45-mi - sample area Willow Flycatcher - USFS (1995) 0.40-mi ¦ USFS (1995) 0.43-mi ¦ USFS (1995) 0.56-mi ¦ USFS (1995) 0.69-mi ¦ USFS (1995) 0.71-mi ¦ USFS (1995) 0.72-mi - sample areas Sierra Marten - CNDDB (1989) 0.69-mi ¦ USFS (1991) 0.28-mi ¦ USFS (1991) 0.47-mi ¦ USFS (1991) 0.88-mi ¦ USFS (1991) 1.00-mi ¦ USFS (1999) 0.46-mi ¦ USFS (2001) 0.59-mi ¦ USFS (2002) 0.50-mi ¦ USFS (2004) 0.50-mi ¦ USFS (2005) 0.50-mi ¦ USFS (2006) 0.50-mi ¦ USFS (2007) 0.50-mi ¦ USFS (2008) 0.50-mi ¦ USFS (2011) 0.75-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located outside of the SNF RCA layer, and approximately 25-ft E a potentially jurisdictional feature (ephemeral drainage) based on desktop analysis of the anticipated work area; however, no impacts to Waters/Wetlands resources are anticipated. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130218002 | a0p4v00000Zw1aq | 17 | 72 | Fir-Red | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.285 | -119.1071 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Great Gray Owl - USFS (2018) 0.56-mi - sample area Willow Flycatcher - USFS (1995) 0.24-mi ¦ USFS (1995) 0.32-mi ¦ USFS (1995) 0.36-mi ¦ USFS (1995) 0.49-mi ¦ USFS (1995) 0.51-mi ¦ USFS (1995) 0.55-mi - sample areas Sierra Marten - CNDDB (1989) 0.77-mi ¦ USFS (1991) 0.28-mi ¦ USFS (1991) 0.35-mi ¦ USFS (1991) 0.86-mi ¦ USFS (1999) 0.36-mi ¦ USFS (2001) 0.78-mi ¦ USFS (2001) 0.83-mi ¦ USFS (2002) 0.67-mi ¦ USFS (2004) 0.67-mi ¦ USFS (2005) 0.67-mi ¦ USFS (2006) 0.67-mi ¦ USFS (2007) 0.67-mi ¦ USFS (2008) 0.67-mi ¦ USFS (2011) 0.96-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located approximately 5-ft E, 105-ft W and within the designated RCA buffer (150 feet on each side, measured from bank full edge) of potentially jurisdictional features (intermittent drainage, and intermittent drainage, respectively) based on desktop analysis of the anticipated work area. None to minimal impacts to Waters/Wetlands resources are anticipated; however, a Waters Monitor is required to be onsite during work activities to ensure adherence to MSUP Protection Measures. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply. W/W Monitor Required.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130218001 | a0p4v00000Zw1VS | 12 | 49 | Aspen-Quaking | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2849 | -119.107 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Great Gray Owl - USFS (2018) 0.56-mi - sample area Willow Flycatcher - USFS (1995) 0.24-mi ¦ USFS (1995) 0.32-mi ¦ USFS (1995) 0.36-mi ¦ USFS (1995) 0.49-mi ¦ USFS (1995) 0.51-mi ¦ USFS (1995) 0.56-mi - sample areas Sierra Marten - CNDDB (1989) 0.78-mi ¦ USFS (1991) 0.28-mi ¦ USFS (1991) 0.35-mi ¦ USFS (1991) 0.86-mi ¦ USFS (1999) 0.36-mi ¦ USFS (2001) 0.78-mi ¦ USFS (2001) 0.83-mi ¦ USFS (2002) 0.67-mi ¦ USFS (2004) 0.67-mi ¦ USFS (2005) 0.67-mi ¦ USFS (2006) 0.67-mi ¦ USFS (2007) 0.67-mi ¦ USFS (2008) 0.67-mi ¦ USFS (2011) 0.95-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located approximately 20-ft E, 90-ft W and within the designated RCA buffer (150 feet on each side, measured from bank full edge) of potentially jurisdictional features (intermittent drainage, and intermittent drainage, respectively) based on desktop analysis of the anticipated work area. None to minimal impacts to Waters/Wetlands resources are anticipated; however, a Waters Monitor is required to be onsite during work activities to ensure adherence to MSUP Protection Measures. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply. W/W Monitor Required.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130218003 | a0p4v00000aXnGI | 18 | 80 | Pine-Lodgepole | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.285 | -119.1068 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Great Gray Owl - USFS (2018) 0.55-mi - sample area Willow Flycatcher - USFS (1995) 0.25-mi ¦ USFS (1995) 0.32-mi ¦ USFS (1995) 0.38-mi ¦ USFS (1995) 0.51-mi ¦ USFS (1995) 0.53-mi ¦ USFS (1995) 0.57-mi - sample areas Sierra Marten - CNDDB (1989) 0.77-mi ¦ USFS (1991) 0.30-mi ¦ USFS (1991) 0.34-mi ¦ USFS (1991) 0.86-mi ¦ USFS (1991) 0.87-mi ¦ USFS (1999) 0.37-mi ¦ USFS (2001) 0.77-mi ¦ USFS (2001) 0.85-mi ¦ USFS (2002) 0.65-mi ¦ USFS (2004) 0.65-mi ¦ USFS (2005) 0.65-mi ¦ USFS (2006) 0.65-mi ¦ USFS (2007) 0.65-mi ¦ USFS (2008) 0.65-mi ¦ USFS (2011) 0.94-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located approximately 40-ft W, 40-ft NW, 80-ft E and within the designated RCA buffer (150 feet on each side, measured from bank full edge) of a potentially jurisdictional features (intermittent drainage, ephemeral drainage, and intermittent drainage, respectively) based on desktop analysis of the anticipated work area; however, no impacts to Waters/Wetlands resources are anticipated. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130238001 | a0p4v00000Zw1b5 | 21 | 72 | Fir-Red | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2798 | -119.1112 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Great Gray Owl - USFS (2018) 0.96-mi - sample area Northern Goshawk - USFS (2013) 0.95-mi Willow Flycatcher - USFS (1995) 0.13-mi ¦ USFS (1995) 0.16-mi ¦ USFS (1995) 0.27-mi ¦ USFS (1995) 0.32-mi ¦ USFS (1995) 0.37-mi ¦ USFS (1995) 0.53-mi ¦ USFS (1997) 0.81-mi - sample areas Sierra Marten - USFS (1978) 0.78-mi ¦ USFS (1991) 0.13-mi ¦ USFS (1991) 0.50-mi ¦ USFS (1991) 0.57-mi ¦ USFS (1991) 0.75-mi ¦ USFS (1999) 0.30-mi ¦ USFS (2001) 0.41-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIA | No W/W resources identified based on desktop review. | No W/W resources identified based on desktop review.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130238002 | a0p4v00000aXnGS | 13 | 52 | Fir | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2798 | -119.1111 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Great Gray Owl - USFS (2018) 0.96-mi - sample area Northern Goshawk - USFS (2013) 0.95-mi Willow Flycatcher - USFS (1995) 0.13-mi ¦ USFS (1995) 0.16-mi ¦ USFS (1995) 0.27-mi ¦ USFS (1995) 0.32-mi ¦ USFS (1995) 0.37-mi ¦ USFS (1995) 0.53-mi ¦ USFS (1997) 0.82-mi - sample areas Sierra Marten - USFS (1978) 0.77-mi ¦ USFS (1991) 0.13-mi ¦ USFS (1991) 0.49-mi ¦ USFS (1991) 0.57-mi ¦ USFS (1991) 0.74-mi ¦ USFS (1999) 0.29-mi ¦ USFS (2001) 0.41-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIA | No W/W resources identified based on desktop review. | No W/W resources identified based on desktop review.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130244006 | a0p4v00000aXo2W | 23 | 83 | Pine-Lodgepole | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2764 | -119.1146 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Northern Goshawk - USFS (2013) 0.65-mi Willow Flycatcher - USFS (1995) 0.35-mi ¦ USFS (1995) 0.42-mi ¦ USFS (1995) 0.43-mi ¦ USFS (1995) 0.45-mi ¦ USFS (1995) 0.48-mi ¦ USFS (1995) 0.67-mi ¦ USFS (1997) 0.70-mi ¦ USFS (1997) 0.85-mi - sample areas Sierra Marten - USFS (1978) 0.47-mi ¦ USFS (1991) 0.35-mi ¦ USFS (1991) 0.43-mi ¦ USFS (1991) 0.83-mi ¦ USFS (1991) 0.84-mi ¦ USFS (1999) 0.53-mi ¦ USFS (2001) 0.12-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located outside of the SNF RCA layer, and approximately 35-ft E a potentially jurisdictional feature (ephemeral drainage) based on desktop analysis of the anticipated work area; however, no impacts to Waters/Wetlands resources are anticipated. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130244005 | a0p4v00000aXo2R | 18 | 75 | Pine-Lodgepole | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2764 | -119.1145 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Northern Goshawk - USFS (2013) 0.66-mi Willow Flycatcher - USFS (1995) 0.35-mi ¦ USFS (1995) 0.42-mi ¦ USFS (1995) 0.43-mi ¦ USFS (1995) 0.44-mi ¦ USFS (1995) 0.48-mi ¦ USFS (1995) 0.67-mi ¦ USFS (1997) 0.70-mi ¦ USFS (1997) 0.86-mi - sample areas Sierra Marten - USFS (1978) 0.48-mi ¦ USFS (1991) 0.35-mi ¦ USFS (1991) 0.42-mi ¦ USFS (1991) 0.83-mi ¦ USFS (1991) 0.84-mi ¦ USFS (1999) 0.53-mi ¦ USFS (2001) 0.13-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located outside of the SNF RCA layer, and approximately 65-ft E a potentially jurisdictional feature (ephemeral drainage) based on desktop analysis of the anticipated work area; however, no impacts to Waters/Wetlands resources are anticipated. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130244004 | a0p4v00000aXnpN | 18 | 73 | Pine-Lodgepole | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2764 | -119.1145 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Northern Goshawk - USFS (2013) 0.65-mi Willow Flycatcher - USFS (1995) 0.35-mi ¦ USFS (1995) 0.42-mi ¦ USFS (1995) 0.43-mi ¦ USFS (1995) 0.44-mi ¦ USFS (1995) 0.48-mi ¦ USFS (1995) 0.67-mi ¦ USFS (1997) 0.70-mi ¦ USFS (1997) 0.86-mi - sample areas Sierra Marten - USFS (1978) 0.47-mi ¦ USFS (1991) 0.35-mi ¦ USFS (1991) 0.43-mi ¦ USFS (1991) 0.83-mi ¦ USFS (1991) 0.84-mi ¦ USFS (1999) 0.53-mi ¦ USFS (2001) 0.12-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located outside of the SNF RCA layer, and approximately 55-ft NE a potentially jurisdictional feature (ephemeral drainage) based on desktop analysis of the anticipated work area; however, no impacts to Waters/Wetlands resources are anticipated. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130244001 | a0p4v00000aXnmE | 24 | 92 | Pine-Lodgepole | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2765 | -119.1143 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Northern Goshawk - USFS (2013) 0.67-mi Willow Flycatcher - USFS (1995) 0.34-mi ¦ USFS (1995) 0.41-mi ¦ USFS (1995) 0.42-mi ¦ USFS (1995) 0.43-mi ¦ USFS (1995) 0.47-mi ¦ USFS (1995) 0.66-mi ¦ USFS (1997) 0.70-mi ¦ USFS (1997) 0.86-mi - sample areas Sierra Marten - USFS (1978) 0.49-mi ¦ USFS (1991) 0.35-mi ¦ USFS (1991) 0.41-mi ¦ USFS (1991) 0.82-mi ¦ USFS (1991) 0.83-mi ¦ USFS (1999) 0.52-mi ¦ USFS (2001) 0.14-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located outside of the SNF RCA layer, and approximately 115-ft NE a potentially jurisdictional feature (ephemeral drainage) based on desktop analysis of the anticipated work area; however, no impacts to Waters/Wetlands resources are anticipated. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130244002 | a0p4v00000aXnmJ | 16 | 92 | Pine-Lodgepole | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2766 | -119.1143 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Northern Goshawk - USFS (2013) 0.67-mi Willow Flycatcher - USFS (1995) 0.34-mi ¦ USFS (1995) 0.41-mi ¦ USFS (1995) 0.42-mi ¦ USFS (1995) 0.43-mi ¦ USFS (1995) 0.47-mi ¦ USFS (1995) 0.66-mi ¦ USFS (1997) 0.70-mi ¦ USFS (1997) 0.86-mi - sample areas Sierra Marten - USFS (1978) 0.49-mi ¦ USFS (1991) 0.35-mi ¦ USFS (1991) 0.41-mi ¦ USFS (1991) 0.82-mi ¦ USFS (1999) 0.52-mi ¦ USFS (2001) 0.14-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located outside of the SNF RCA layer, and approximately 125-ft NE a potentially jurisdictional feature (ephemeral drainage) based on desktop analysis of the anticipated work area; however, no impacts to Waters/Wetlands resources are anticipated. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130244003 | a0p4v00000aXnkn | 17 | 61 | Pine-Lodgepole | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2764 | -119.1144 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Northern Goshawk - USFS (2013) 0.66-mi Willow Flycatcher - USFS (1995) 0.35-mi ¦ USFS (1995) 0.42-mi ¦ USFS (1995) 0.43-mi ¦ USFS (1995) 0.44-mi ¦ USFS (1995) 0.48-mi ¦ USFS (1995) 0.67-mi ¦ USFS (1997) 0.70-mi ¦ USFS (1997) 0.86-mi - sample areas Sierra Marten - USFS (1978) 0.48-mi ¦ USFS (1991) 0.35-mi ¦ USFS (1991) 0.42-mi ¦ USFS (1991) 0.82-mi ¦ USFS (1991) 0.84-mi ¦ USFS (1999) 0.53-mi ¦ USFS (2001) 0.13-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located outside of the SNF RCA layer, and approximately 70-ft NE a potentially jurisdictional feature (ephemeral drainage) based on desktop analysis of the anticipated work area; however, no impacts to Waters/Wetlands resources are anticipated. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130248001 | a0p4v00000aXnmT | 25 | 103 | Fir-Red | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2744 | -119.1172 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Northern Goshawk - USFS (1997) 0.97-mi ¦ USFS (2000) 0.97-mi ¦ USFS (2013) 0.45-mi Willow Flycatcher - USFS (1995) 0.47-mi ¦ USFS (1995) 0.56-mi ¦ USFS (1995) 0.60-mi ¦ USFS (1995) 0.61-mi ¦ USFS (1995) 0.63-mi ¦ USFS (1995) 0.79-mi ¦ USFS (1997) 0.66-mi ¦ USFS (1997) 0.76-mi - sample areas Sierra Marten - USFS (1978) 0.28-mi ¦ USFS (1991) 0.41-mi ¦ USFS (1991) 0.62-mi ¦ USFS (1991) 0.82-mi ¦ USFS (1991) 0.96-mi ¦ USFS (1999) 0.73-mi ¦ USFS (2001) 0.12-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located outside of the SNF RCA layer, and approximately 85-ft W a potentially jurisdictional feature (ephemeral drainage) based on desktop analysis of the anticipated work area; however, no impacts to Waters/Wetlands resources are anticipated. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130260001 | a0p4v00000aXo30 | 13 | 42 | Pine-Lodgepole | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2703 | -119.1213 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Northern Goshawk - USFS (1997) 0.95-mi ¦ USFS (2000) 0.93-mi ¦ USFS (2013) 0.09-mi Willow Flycatcher - USFS (1995) 0.78-mi ¦ USFS (1995) 0.89-mi ¦ USFS (1995) 0.92-mi ¦ USFS (1995) 0.95-mi ¦ USFS (1995) 0.97-mi ¦ USFS (1997) 0.69-mi ¦ USFS (1997) 0.75-mi - sample areas Sierra Marten - USFS (1978) 0.07-mi ¦ USFS (1991) 0.54-mi ¦ USFS (1991) 0.63-mi ¦ USFS (1991) 0.77-mi ¦ USFS (1991) 0.98-mi ¦ USFS (2001) 0.45-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located approximately 65-ft NE and within the designated RCA buffer (150 feet on each side, measured from bank full edge) a potentially jurisdictional feature (ephemeral drainage) based on desktop analysis of the anticipated work area; however, no impacts to Waters/Wetlands resources are anticipated. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130263001 | a0p4v00000Zw1b0 | 13 | 55 | Pine-Lodgepole | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2816 | -119.11 | Sierra Nevada Yellow-Legged Frog - SNF Unknown occupied Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Great Gray Owl - USFS (2018) 0.82-mi - sample area Willow Flycatcher - USFS (1995) ¦ USFS (1995) 0.14-mi ¦ USFS (1995) 0.28-mi ¦ USFS (1995) 0.32-mi ¦ USFS (1995) 0.37-mi ¦ USFS (1995) 0.49-mi ¦ USFS (1997) 0.87-mi - sample areas Sierra Marten - USFS (1978) 0.91-mi ¦ USFS (1991) 0.01-mi ¦ USFS (1991) 0.48-mi ¦ USFS (1991) 0.61-mi ¦ USFS (1991) 0.77-mi ¦ USFS (1999) 0.26-mi ¦ USFS (2001) 0.55-mi ¦ USFS (2002) 0.95-mi ¦ USFS (2004) 0.95-mi ¦ USFS (2005) 0.95-mi ¦ USFS (2006) 0.95-mi ¦ USFS (2007) 0.95-mi ¦ USFS (2008) 0.95-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located within, 45-ft S, 50-ft SW and within the designated RCA buffer (300 feet from edge of feature or riparian vegetation, whichever width is greater) of potentially jurisdictional features (freshwater forested/shrub wetland, intermittent drainage, and SNF meadow [516M341], respectively) based on desktop analysis of the anticipated work area. None to minimal impacts to Waters/Wetlands resources are anticipated; however, a Waters Monitor is required to be onsite during work activities to ensure adherence to MSUP Protection Measures. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply. W/W Monitor Required.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130264001 | a0p4v00000Zw1YH | 21 | 83 | Pine-Lodgepole | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2821 | -119.1094 | Sierra Nevada Yellow-Legged Frog - SNF Unknown occupied Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Great Gray Owl - USFS (2018) 0.78-mi - sample area Willow Flycatcher - USFS (1995) 0.01-mi ¦ USFS (1995) 0.17-mi ¦ USFS (1995) 0.25-mi ¦ USFS (1995) 0.35-mi ¦ USFS (1995) 0.39-mi ¦ USFS (1995) 0.50-mi ¦ USFS (1997) 0.91-mi - sample areas Sierra Marten - CNDDB (1989) 0.97-mi ¦ USFS (1978) 0.96-mi ¦ USFS (1991) 0.05-mi ¦ USFS (1991) 0.44-mi ¦ USFS (1991) 0.65-mi ¦ USFS (1991) 0.77-mi ¦ USFS (1999) 0.26-mi ¦ USFS (2001) 0.60-mi ¦ USFS (2002) 0.90-mi ¦ USFS (2004) 0.90-mi ¦ USFS (2005) 0.90-mi ¦ USFS (2006) 0.90-mi ¦ USFS (2007) 0.90-mi ¦ USFS (2008) 0.90-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located approximately 35-ft W, 95-ft NE and within the designated RCA buffer (300 feet from edge of feature or riparian vegetation, whichever width is greater) of potentially jurisdictional features (intermittent drainage, and SNF meadow [516M341], respectively) based on desktop analysis of the anticipated work area. None to minimal impacts to Waters/Wetlands resources are anticipated; however, a Waters Monitor is required to be onsite during work activities to ensure adherence to MSUP Protection Measures. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply. W/W Monitor Required.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130268001 | a0p4v00000aXnpm | 14 | 79 | Pine-Lodgepole | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2742 | -119.1171 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Northern Goshawk - USFS (1997) 0.97-mi ¦ USFS (2000) 0.97-mi ¦ USFS (2013) 0.45-mi Willow Flycatcher - USFS (1995) 0.48-mi ¦ USFS (1995) 0.57-mi ¦ USFS (1995) 0.61-mi ¦ USFS (1995) 0.62-mi ¦ USFS (1995) 0.63-mi ¦ USFS (1995) 0.80-mi ¦ USFS (1997) 0.67-mi ¦ USFS (1997) 0.76-mi - sample areas Sierra Marten - USFS (1978) 0.27-mi ¦ USFS (1991) 0.40-mi ¦ USFS (1991) 0.63-mi ¦ USFS (1991) 0.82-mi ¦ USFS (1991) 0.95-mi ¦ USFS (1999) 0.73-mi ¦ USFS (2001) 0.12-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located outside of the SNF RCA layer, and approximately 55-ft W of a potentially jurisdictional feature (ephemeral drainage) based on desktop analysis of the anticipated work area; however, no impacts to Waters/Wetlands resources are anticipated. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130316001 | a0p4v00000aXnGN | 25 | 89 | Fir-Red | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2843 | -119.1076 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Great Gray Owl - USFS (2018) 0.61-mi - sample area Willow Flycatcher - USFS (1995) 0.18-mi ¦ USFS (1995) 0.29-mi ¦ USFS (1995) 0.31-mi ¦ USFS (1995) 0.45-mi ¦ USFS (1995) 0.48-mi ¦ USFS (1995) 0.54-mi - sample areas Sierra Marten - CNDDB (1989) 0.82-mi ¦ USFS (1991) 0.23-mi ¦ USFS (1991) 0.36-mi ¦ USFS (1991) 0.81-mi ¦ USFS (1991) 0.83-mi ¦ USFS (1999) 0.33-mi ¦ USFS (2001) 0.78-mi ¦ USFS (2001) 0.83-mi ¦ USFS (2002) 0.72-mi ¦ USFS (2004) 0.72-mi ¦ USFS (2005) 0.72-mi ¦ USFS (2006) 0.72-mi ¦ USFS (2007) 0.72-mi ¦ USFS (2008) 0.72-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located approximately 150-ft NW and within the designated RCA buffer (150 feet on each side, measured from bank full edge) of a potentially jurisdictional feature (intermittent drainage) based on desktop analysis of the anticipated work area; however, no impacts to Waters/Wetlands resources are anticipated. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130319001 | a0p4v00000Zw1Zi | 15 | 89 | Pine-Lodgepole | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2853 | -119.1064 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Great Gray Owl - USFS (2018) 0.53-mi - sample area Willow Flycatcher - USFS (1995) 0.28-mi ¦ USFS (1995) 0.33-mi ¦ USFS (1995) 0.41-mi ¦ USFS (1995) 0.53-mi ¦ USFS (1995) 0.55-mi ¦ USFS (1995) 0.58-mi - sample areas Sierra Marten - CNDDB (1989) 0.75-mi ¦ USFS (1991) 0.32-mi ¦ USFS (1991) 0.34-mi ¦ USFS (1991) 0.87-mi ¦ USFS (1991) 0.89-mi ¦ USFS (1999) 0.38-mi ¦ USFS (2001) 0.74-mi ¦ USFS (2001) 0.87-mi ¦ USFS (2002) 0.63-mi ¦ USFS (2004) 0.63-mi ¦ USFS (2005) 0.63-mi ¦ USFS (2006) 0.63-mi ¦ USFS (2007) 0.63-mi ¦ USFS (2008) 0.63-mi ¦ USFS (2011) 0.92-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located approximately 25-ft E, 75-ft NW and within the designated RCA buffer (150 feet on each side, measured from bank full edge) of potentially jurisdictional features (intermittent drainage, and ephemeral drainage, respectively) based on desktop analysis of the anticipated work area. None to minimal impacts to Waters/Wetlands resources are anticipated; however, a Waters Monitor is required to be onsite during work activities to ensure adherence to MSUP Protection Measures. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply. W/W Monitor Required.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130343004 | a0p4v00000aXo2C | 25 | 86 | Pine-Lodgepole | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2767 | -119.1144 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Northern Goshawk - USFS (2013) 0.68-mi Willow Flycatcher - USFS (1995) 0.33-mi ¦ USFS (1995) 0.40-mi ¦ USFS (1995) 0.41-mi ¦ USFS (1995) 0.43-mi ¦ USFS (1995) 0.46-mi ¦ USFS (1995) 0.65-mi ¦ USFS (1997) 0.70-mi ¦ USFS (1997) 0.86-mi - sample areas Sierra Marten - USFS (1978) 0.50-mi ¦ USFS (1991) 0.37-mi ¦ USFS (1991) 0.40-mi ¦ USFS (1991) 0.82-mi ¦ USFS (1991) 0.83-mi ¦ USFS (1999) 0.52-mi ¦ USFS (2001) 0.15-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located outside of the SNF RCA layer, and approximately 135-ft NE of a potentially jurisdictional feature (ephemeral drainage) based on desktop analysis of the anticipated work area; however, no impacts to Waters/Wetlands resources are anticipated. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130343003 | a0p4v00000aXo27 | 24 | 85 | Pine-Lodgepole | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2767 | -119.1143 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Northern Goshawk - USFS (2013) 0.68-mi Willow Flycatcher - USFS (1995) 0.33-mi ¦ USFS (1995) 0.40-mi ¦ USFS (1995) 0.41-mi ¦ USFS (1995) 0.43-mi ¦ USFS (1995) 0.46-mi ¦ USFS (1995) 0.65-mi ¦ USFS (1997) 0.70-mi ¦ USFS (1997) 0.86-mi - sample areas Sierra Marten - USFS (1978) 0.50-mi ¦ USFS (1991) 0.36-mi ¦ USFS (1991) 0.40-mi ¦ USFS (1991) 0.82-mi ¦ USFS (1999) 0.51-mi ¦ USFS (2001) 0.15-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIA | No W/W resources identified based on desktop review. | No W/W resources identified based on desktop review.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130343002 | a0p4v00000aXnpJ | 15 | 67 | Pine-Lodgepole | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2769 | -119.1144 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Northern Goshawk - USFS (2013) 0.69-mi Willow Flycatcher - USFS (1995) 0.31-mi ¦ USFS (1995) 0.39-mi ¦ USFS (1995) 0.40-mi ¦ USFS (1995) 0.43-mi ¦ USFS (1995) 0.45-mi ¦ USFS (1995) 0.64-mi ¦ USFS (1997) 0.69-mi ¦ USFS (1997) 0.86-mi - sample areas Sierra Marten - USFS (1978) 0.51-mi ¦ USFS (1991) 0.38-mi ¦ USFS (1991) 0.39-mi ¦ USFS (1991) 0.81-mi ¦ USFS (1991) 0.83-mi ¦ USFS (1999) 0.51-mi ¦ USFS (2001) 0.16-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIA | No W/W resources identified based on desktop review. | No W/W resources identified based on desktop review.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130343001 | a0p4v00000aXnl3 | 17 | 69 | Pine-Lodgepole | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2769 | -119.1144 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Northern Goshawk - USFS (2013) 0.69-mi Willow Flycatcher - USFS (1995) 0.31-mi ¦ USFS (1995) 0.39-mi ¦ USFS (1995) 0.40-mi ¦ USFS (1995) 0.43-mi ¦ USFS (1995) 0.45-mi ¦ USFS (1995) 0.64-mi ¦ USFS (1997) 0.69-mi ¦ USFS (1997) 0.86-mi - sample areas Sierra Marten - USFS (1978) 0.51-mi ¦ USFS (1991) 0.38-mi ¦ USFS (1991) 0.39-mi ¦ USFS (1991) 0.81-mi ¦ USFS (1991) 0.83-mi ¦ USFS (1999) 0.51-mi ¦ USFS (2001) 0.16-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIA | No W/W resources identified based on desktop review. | No W/W resources identified based on desktop review.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130349003 | a0p4v00000aXo1s | 21 | 100 | Pine-Lodgepole | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2781 | -119.1124 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Northern Goshawk - USFS (2013) 0.82-mi Willow Flycatcher - USFS (1995) 0.24-mi ¦ USFS (1995) 0.27-mi ¦ USFS (1995) 0.32-mi ¦ USFS (1995) 0.36-mi ¦ USFS (1995) 0.42-mi ¦ USFS (1995) 0.59-mi ¦ USFS (1997) 0.77-mi ¦ USFS (1997) 0.96-mi - sample areas Sierra Marten - USFS (1978) 0.64-mi ¦ USFS (1991) 0.27-mi ¦ USFS (1991) 0.40-mi ¦ USFS (1991) 0.68-mi ¦ USFS (1991) 0.75-mi ¦ USFS (1999) 0.38-mi ¦ USFS (2001) 0.28-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located outside of the SNF RCA layer, and approximately 50-ft W of a potentially jurisdictional feature (ephemeral drainage) based on desktop analysis of the anticipated work area; however, no impacts to Waters/Wetlands resources are anticipated. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130349002 | a0p4v00000aXnoy | 29 | 92 | Fir-Red | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2785 | -119.1122 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Northern Goshawk - USFS (2013) 0.84-mi Willow Flycatcher - USFS (1995) 0.21-mi ¦ USFS (1995) 0.24-mi ¦ USFS (1995) 0.31-mi ¦ USFS (1995) 0.34-mi ¦ USFS (1995) 0.40-mi ¦ USFS (1995) 0.58-mi ¦ USFS (1997) 0.77-mi ¦ USFS (1997) 0.96-mi - sample areas Sierra Marten - USFS (1978) 0.67-mi ¦ USFS (1991) 0.24-mi ¦ USFS (1991) 0.42-mi ¦ USFS (1991) 0.66-mi ¦ USFS (1991) 0.75-mi ¦ USFS (1999) 0.36-mi ¦ USFS (2001) 0.30-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located outside of the SNF RCA layer, and approximately 20-ft E of a potentially jurisdictional feature (ephemeral drainage) based on desktop analysis of the anticipated work area; however, no impacts to Waters/Wetlands resources are anticipated. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130349001 | a0p4v00000aXnlz | 14 | 78 | Pine-Lodgepole | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2781 | -119.1123 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Northern Goshawk - USFS (2013) 0.82-mi Willow Flycatcher - USFS (1995) 0.24-mi ¦ USFS (1995) 0.27-mi ¦ USFS (1995) 0.31-mi ¦ USFS (1995) 0.36-mi ¦ USFS (1995) 0.42-mi ¦ USFS (1995) 0.60-mi ¦ USFS (1997) 0.77-mi ¦ USFS (1997) 0.96-mi - sample areas Sierra Marten - USFS (1978) 0.64-mi ¦ USFS (1991) 0.27-mi ¦ USFS (1991) 0.39-mi ¦ USFS (1991) 0.68-mi ¦ USFS (1991) 0.75-mi ¦ USFS (1999) 0.38-mi ¦ USFS (2001) 0.28-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located approximately 55-ft W and within the designated RCA buffer (150 feet on each side, measured from bank full edge) of a potentially jurisdictional feature (ephemeral drainage) based on desktop analysis of the anticipated work area; however, no impacts to Waters/Wetlands resources are anticipated. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130350001 | a0p4v00000Zw1al | 28 | 87 | Fir-Red | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2856 | -119.1049 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Great Gray Owl - USFS (2018) 0.51-mi - sample area Willow Flycatcher - USFS (1995) 0.35-mi ¦ USFS (1995) 0.36-mi ¦ USFS (1995) 0.49-mi ¦ USFS (1995) 0.62-mi ¦ USFS (1995) 0.64-mi ¦ USFS (1995) 0.66-mi - sample areas Sierra Marten - CNDDB (1989) 0.73-mi ¦ USFS (1991) 0.29-mi ¦ USFS (1991) 0.40-mi ¦ USFS (1991) 0.86-mi ¦ USFS (1991) 0.94-mi ¦ USFS (1999) 0.41-mi ¦ USFS (2001) 0.66-mi ¦ USFS (2001) 0.94-mi ¦ USFS (2002) 0.56-mi ¦ USFS (2004) 0.56-mi ¦ USFS (2005) 0.56-mi ¦ USFS (2006) 0.56-mi ¦ USFS (2007) 0.56-mi ¦ USFS (2008) 0.56-mi ¦ USFS (2011) 0.83-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located outside of the SNF RCA layer, and approximately 85-ft NW of a potentially jurisdictional feature (ephemeral drainage) based on desktop analysis of the anticipated work area; however, no impacts to Waters/Wetlands resources are anticipated. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130405001 | a0p4v00000aXoZk | 12 | 61 | Pine-Lodgepole | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2688 | -119.1217 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Northern Goshawk - USFS (2000) 0.98-mi ¦ USFS (2013) 0.03-mi Willow Flycatcher - USFS (1995) 0.88-mi ¦ USFS (1995) 0.99-mi ¦ USFS (1997) 0.77-mi ¦ USFS (1997) 0.82-mi - sample areas Sierra Marten - CNDDB (1989) 0.92-mi ¦ USFS (1978) 0.17-mi ¦ USFS (1991) 0.52-mi ¦ USFS (1991) 0.69-mi ¦ USFS (1991) 0.70-mi ¦ USFS (2001) 0.54-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIA | No W/W resources identified based on desktop review. | No W/W resources identified based on desktop review.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130405003 | a0p4v00000aXou9 | 15 | 61 | Pine-Lodgepole | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2688 | -119.1218 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Northern Goshawk - USFS (2000) 0.98-mi ¦ USFS (2013) 0.03-mi Willow Flycatcher - USFS (1995) 0.89-mi ¦ USFS (1995) 1.00-mi ¦ USFS (1997) 0.77-mi ¦ USFS (1997) 0.82-mi - sample areas Sierra Marten - CNDDB (1989) 0.92-mi ¦ USFS (1978) 0.17-mi ¦ USFS (1991) 0.52-mi ¦ USFS (1991) 0.69-mi ¦ USFS (1991) 0.70-mi ¦ USFS (2001) 0.54-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIA | No W/W resources identified based on desktop review. | No W/W resources identified based on desktop review.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130405002 | a0p4v00000aXok9 | 29 | 81 | Pine-Lodgepole | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2687 | -119.1219 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Northern Goshawk - USFS (2000) 0.98-mi ¦ USFS (2013) 0.03-mi Willow Flycatcher - USFS (1995) 0.89-mi ¦ USFS (1997) 0.77-mi ¦ USFS (1997) 0.82-mi - sample areas Sierra Marten - CNDDB (1989) 0.91-mi ¦ USFS (1978) 0.18-mi ¦ USFS (1991) 0.52-mi ¦ USFS (1991) 0.69-mi ¦ USFS (1991) 0.70-mi ¦ USFS (2001) 0.55-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIA | No W/W resources identified based on desktop review. | No W/W resources identified based on desktop review.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130418001 | a0p4v00000aXoZp | 16 | 84 | Pine-Lodgepole | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2695 | -119.1224 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Northern Goshawk - USFS (1997) 0.96-mi ¦ USFS (2000) 0.92-mi ¦ USFS (2013) 0.02-mi Willow Flycatcher - USFS (1995) 0.85-mi ¦ USFS (1995) 0.96-mi ¦ USFS (1995) 0.99-mi ¦ USFS (1997) 0.71-mi ¦ USFS (1997) 0.76-mi - sample areas Sierra Marten - CNDDB (1989) 0.97-mi ¦ USFS (1978) 0.16-mi ¦ USFS (1991) 0.48-mi ¦ USFS (1991) 0.69-mi ¦ USFS (1991) 0.71-mi ¦ USFS (2001) 0.53-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIA | No W/W resources identified based on desktop review. | No W/W resources identified based on desktop review.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | H05130418002 | a0p4v00000aXouE | 23 | 80 | Pine-Lodgepole | 1 | Dead Hazard Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2695 | -119.1224 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Northern Goshawk - USFS (1997) 0.96-mi ¦ USFS (2000) 0.92-mi ¦ USFS (2013) 0.02-mi Willow Flycatcher - USFS (1995) 0.85-mi ¦ USFS (1995) 0.96-mi ¦ USFS (1995) 0.99-mi ¦ USFS (1997) 0.71-mi ¦ USFS (1997) 0.76-mi - sample areas Sierra Marten - CNDDB (1989) 0.97-mi ¦ USFS (1978) 0.16-mi ¦ USFS (1991) 0.48-mi ¦ USFS (1991) 0.69-mi ¦ USFS (1991) 0.71-mi ¦ USFS (2001) 0.54-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIA | No W/W resources identified based on desktop review. | No W/W resources identified based on desktop review.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | R05136164010 | a0p4v00000aXo2q | 22 | 92 | Pine-Lodgepole | 1 | Green Routine Line Clearing Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2738 | -119.118 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Northern Goshawk - USFS (1997) 0.95-mi ¦ USFS (2000) 0.94-mi ¦ USFS (2013) 0.39-mi Willow Flycatcher - USFS (1995) 0.51-mi ¦ USFS (1995) 0.61-mi ¦ USFS (1995) 0.65-mi ¦ USFS (1995) 0.68-mi ¦ USFS (1995) 0.69-mi ¦ USFS (1995) 0.84-mi ¦ USFS (1997) 0.66-mi ¦ USFS (1997) 0.73-mi - sample areas Sierra Marten - USFS (1978) 0.21-mi ¦ USFS (1991) 0.44-mi ¦ USFS (1991) 0.69-mi ¦ USFS (1991) 0.77-mi ¦ USFS (1999) 0.79-mi ¦ USFS (2001) 0.18-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located approximately 65-ft NE and within the designated RCA buffer (150 feet on each side, measured from bank full edge) of a potentially jurisdictional feature (intermittent drainage) based on desktop analysis of the anticipated work area; however, no impacts to Waters/Wetlands resources are anticipated. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | R05136224001 | a0p4v00000aXnpX | 13 | 31 | Pine-Lodgepole | 1 | Green Routine Line Clearing Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2761 | -119.1148 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Northern Goshawk - USFS (2013) 0.63-mi Willow Flycatcher - USFS (1995) 0.37-mi ¦ USFS (1995) 0.45-mi ¦ USFS (1995) 0.47-mi ¦ USFS (1995) 0.50-mi ¦ USFS (1995) 0.69-mi ¦ USFS (1997) 0.70-mi ¦ USFS (1997) 0.84-mi - sample areas Sierra Marten - USFS (1978) 0.45-mi ¦ USFS (1991) 0.35-mi ¦ USFS (1991) 0.45-mi ¦ USFS (1991) 0.84-mi ¦ USFS (1991) 0.86-mi ¦ USFS (1991) 0.99-mi ¦ USFS (1999) 0.56-mi ¦ USFS (2001) 0.10-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located outside of the SNF RCA layer, and approximately 70-ft W of a potentially jurisdictional feature (ephemeral drainage) based on desktop analysis of the anticipated work area; however, no impacts to Waters/Wetlands resources are anticipated. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply.
MSUP_00595_SNF_VM_IIC | Sierra National Forest | High Sierra Ranger District | IIC | 50 | Kaiser Pass -Badger Flat | R05136281001 | a0p4v00000aXnmO | 11 | 22 | Fir-Red | 1 | Green Routine Line Clearing Tree Removal | Immediately upon USFS Approval (weather permitting) | None | Work area will be accessed from existing roads, where feasible; however, removal of logs and large quantities of woody debris may require overland travel of skid steers, skidders, grapple trucks, sennebogens, chippers, and/or other types of hauling equipment to and from tree removal locations. Where possible, existing skid roads and disturbed areas will be used for overland travel and when creating new skid roads SCE will adhere to the Overland Travel Route (OTR) Measures (See Additional Measures Tab). | Trees will be cut and managed with various power and hand tools (e.g., chain saws, brush cutters, pruners, and chipper). Where feasible, all material will be removed from the work area and hauled to a disposal site for chipping or air curtain burner consumption. Merchantable logs can be relocated to Forest-approved decking locations, where requested. Where the removal of large logs is infeasible due to terrain and access issues, limbs will be removed and boles will be bucked to lay flat and left onsite in a manner that avoids sensitive resources. Specific means and methods for tree removal vary by location and are determined by several factors (e.g., tree condition and structural features, site considerations, resource avoidance measures, crew expertise, safety). Crews may use cranes, bucket trucks, spider lifts, skid steers, skidders, sennebogens, chippers, and/or grapple trucks to cut trees and manage logs and slash. | 37.2761 | -119.1149 | Yosemite Toad - SNF Occupied ¦ USFWS Critical Habitat Acorn Woodpecker - Outside of ACWO Polygon Northern Goshawk - USFS (2013) 0.62-mi Willow Flycatcher - USFS (1995) 0.37-mi ¦ USFS (1995) 0.45-mi ¦ USFS (1995) 0.47-mi ¦ USFS (1995) 0.50-mi ¦ USFS (1995) 0.69-mi ¦ USFS (1997) 0.69-mi ¦ USFS (1997) 0.84-mi - sample areas Sierra Marten - USFS (1978) 0.45-mi ¦ USFS (1991) 0.35-mi ¦ USFS (1991) 0.46-mi ¦ USFS (1991) 0.84-mi ¦ USFS (1991) 0.87-mi ¦ USFS (1991) 0.99-mi ¦ USFS (1999) 0.56-mi ¦ USFS (2001) 0.10-mi | POTENTIAL TO OCCUR: |  | Cultural resource reviews and protection measures are reported in the confidential heritage notification table. | IIB | Tree is located outside of the SNF RCA layer, and approximately 90-ft W of a potentially jurisdictional feature (ephemeral drainage) based on desktop analysis of the anticipated work area; however, no impacts to Waters/Wetlands resources are anticipated. | MSUP Protection Measures: OMP BMPs C.1-6, C.9-15 Apply.